## Sheet1
Item | Estimated time | Notes
Tasks tab
Filter by Customer (not sorting) | 8 days
Filter by assignee = user vs usergroup. Sorting would be fine too. | 6 days
Filter/Sort by progress (would replace the previous one) | 20-30 days
See wordcount before accepting task (not matched - see from metrics) | 4 days
Security, Editor
Proofreader can see the translator’s name in the Editor | Available | AVAILABLE - configuration > settings> privacy Settings are global, not possible to change per user role.
User profile > tab tasks or rating
See summary of tasks finished & words processed by user (similar as in Punctuality) | 9 days (without sorting by wordcount) or 15 days (with sorting)
Advanced search
Search by language status, not overall project. | Available | Flag for searching only in language combinations for workflow status dropdown.
Filter per user group | 6 days
Translation flows
Bulk changes: search by multiple project names | 5 days | RegEx Search For example: String1¦string2¦string3 - not permitted character in project name as separator.
Projects view: add column task assignee | 12 days | We need to do more than display users, as this will also have to work for complex workflows with multiple users and languages
Data Points
Dashboards / Reporting: Words/tasks translated all languages Words translated per language Words translated per user Accrued cost & forecast costs We do have dashboards showing costs generated (division to finished / non finished) for the project but nothing for estimations (I understand that this “forecast cost”). Number of tasks pending per language Number of tasks completed vs time Automated time tracking - ok Average resolution time per task - creation to first completion Workflow dates per language Error reporting statistics/quality scores per user/language Words processed vs words received Time range, how many word were sent and how many were completed Average time taken per individual task - open - to finish Quality failed tasks after LQA per language / freelancer / proofreader | 40 days | SUMMARY FOR NEW TYPE OF REPORT: Words / tasks translated all languages / per language / per user (I think we need here also division per task because it is required below) Number of tasks pending - we should resist it on Min/max status (checkbox "Include only pending tasks - all tasks that are not finished) - There should be automatic time tracking included "Average resolution time per task - creation to first completion" and "Average time taken per individual task - open - to finish" - time from the start of the workflow to the finish. It must include times for tasks that were done before Continuous project and Reanalysis (we have to store this data). Words processes vs words received - we need time range here. Report should show how many words were sent and how many were completed (Done / To be done / Total)