## Sheet1
Task | Days | Start Date | End Date | Responsible | Comment from adidas
Adidas PO | 1 | 2018-01-31 | 2018-02-01 | Adidas
Adidas Developments Stage 1 | 119 | 2018-01-01 | 2018-04-30 | XTM Dev
Adidas QA and Feedback on Stage 1 | 14 | 2018-05-01 | 2018-05-15 | Adidas
XTM Dev fixes | 14 | 2018-05-15 | 2018-05-29 | XTM Dev
Provision of Server Hardware | 10 | 2018-02-01 | 2018-02-11 | XTM Sys Admin
Installation of OS and CDN etc | 10 | 2018-02-12 | 2018-02-22 | XTM Sys Admin
XTM System Installation - Production Instance | 3 | 2018-02-22 | 2018-02-25 | XTM Sys Admin
XTM System Installation - Non Production Instance | 3 | 2018-02-22 | 2018-02-25 | XTM Sys Admin
Filter customizaton | 8 | 2018-03-05 | 2018-03-13 | XTM/Adidas | Action Item adidas: provide input to XTM about the needed Analysis Templates for Multilingual excel projects, deadline March 5
XTM Live / Initial Online live Training Session for Admin's | 5 | 2018-03-05 | 2018-03-10 | XTM - Mikolaj
XTM Live / Initial Online live Training Session for PM's | 5 | 2018-03-05 | 2018-03-10 | XTM - Mikolaj
XTM Live /Initial Online live Training Session for Translators | 5 | 2018-03-05 | 2018-03-10 | XTM - Mikolaj
XTM Live /Initial Online live Training Session for ICR's | 5 | 2018-03-05 | 2018-03-10 | XTM - Mikolaj
XTM Live /Initial Online live Training Session for LSP's | 5 | 2018-03-05 | 2018-03-10 | XTM - Mikolaj | May or may not be needed
User & LSP Setup | 5 | 2018-03-10 | 2018-03-15 | Adidas - XTM Mikolaj | Dates are fine, please plan a call before mid-february to discuss users migration options from WS to XTM
Customer Structure Setup | 2 | 2018-03-10 | 2018-03-12 | Adidas - XTM Mikolaj
Adidas to Provide existing TM and Terminology data | 5 | 2018-03-10 | 2018-03-15 | Adidas | Dates are fine, please plan a call before mid-february to discuss TM migration options and make it as effective as possible
WS to XTM Initial TM porting - TMX | 20 | 2018-04-05 | 2018-04-25 | XTM - Mikolaj
Initial Ratecard Setup - LSP /Users | 5 | 2018-03-10 | 2018-03-15 | Adidas - XTM Mikolaj | Finalizing this step could require more time than planned due to data collection and rate cards actual set-up, however it is not critical until we start working real PROD projects
Workflow Setup, setup and configuration | 35 | 2018-03-25 | 2018-04-29 | Adidas - XTM Mikolaj
Workflow Template estabilishment | 21 | 2018-04-29 | 2018-05-20 | Adidas - XTM Mikolaj
Worklow Optimization | 60 | 2018-04-05 | 2018-06-04 | Adidas - XTM Mikolaj
LQA Setup and Configuration | 21 | 2018-04-12 | 2018-05-03 | Adidas - XTM Mikolaj
Adidas Developments Stage 2 | 60 | 2018-05-01 | 2018-06-30 | XTM Dev
Adidas QA and Feedback on Stage2 | 14 | 2018-07-01 | 2018-07-15 | Adidas
XTM Dev fixes Stage 2 | 14 | 2018-07-15 | 2018-07-29 | XTM Dev
TM nd Terminology Update and Source content Scripting - TM Optimization | 15 | 2018-06-15 | 2018-06-30 | XTM - Mikolaj
Advanced Online live Training Session for Admin's | 5 | 2018-07-02 | 2018-07-07 | XTM - Mikolaj | 1. This advanced training should instruct users about our MUST HAVE customised features as well, planned to be delivered on June 30. 2. Training about the ICR process should be given to Translators, usually they are the ones instructing the Reviewers on site at adidas 3. Very likely we won't set up or use subcontractors/LSPs, in any case this advanced training should be provided to PMs/Admin. It will help evaluating the need of LSPs set-up in the final config.
Advanced Online live Training Session for PM's | 5 | 2018-07-02 | 2018-07-07 | XTM - Mikolaj
Advanced Online live Training Session for Translators | 5 | 2018-07-02 | 2018-07-07 | XTM - Mikolaj
Advanced Online live Training Session for ICR's | 5 | 2018-07-02 | 2018-07-07 | XTM - Mikolaj
TM nd Terminology Update and Source update 3 | 5 | 2018-08-09 | 2018-08-14 | XTM
XTM Go Live |  | 2018-08-15 |  | XTM/Adidas
XTM Custom Dev Stage 3 | 114 | 2018-06-30 | 2018-10-22 | XTM
Adidas QA and Feedback on Stage 3 | 14 | 2018-10-22 | 2018-11-05 | Adidas
XTM Dev fixes | 14 | 2018-11-05 | 2018-11-19 | XTM Dev
Advanced Online live Training Session for Admin's | 5 | 2018-10-01 | 2018-10-06 | XTM - Mikolaj | For this 3rd round of trainings, ICR and LSP sessions could be unnecessary, based on the previous 2 training rounds.
Advanced Online live Training Session for PM's | 5 | 2018-10-01 | 2018-10-06 | XTM - Mikolaj
Advanced Online live Training Session for Translators | 5 | 2018-10-01 | 2018-10-06 | XTM - Mikolaj
Advanced Online live Training Session for ICR's | 5 | 2018-10-01 | 2018-10-06 | XTM - Mikolaj
Advanced Online live Training Session for LSP's | 5 | 2018-10-01 | 2018-10-06 | XTM - Mikolaj
Formulas:
End Date = [Days]+[Start Date]